## Sheet1
TASKS |  |  | DATES
Team
| Ripdaman | Diya | March 2022
| Charles | Mayank | 11 | 14 | 17 | 20 | 23 | 26 | 29 | 31 | 7
Discuss the Project Topic |  |  | March 2022 14: (TEAM)
Finalize Project Objective |  |  | March 2022 17: (TEAM)
Finalize Project Components |  |  | March 2022 20: (TEAM)
Code individual Components |  |  | March 2022 26: (Diya)
Combine code |  |  | March 2022 26: (Charles)
Assemble components - Breadboard |  |  | March 2022 26: (Mayank)
Assemble components - Solder |  |  | March 2022 23: (Ripdaman)
Final Hardware Testing |  |  | March 2022 26: (Mayank)
Finalize Tech Stack |  |  | March 2022 26: (Charles)
Work on Front End |  |  | March 2022 26: (Diya)
Work on Back End |  |  | March 2022 29: (Ripdaman)
Combine Front and Back End |  |  | March 2022 31: (Ripdaman)
Unit Testing |  |  | March 2022 31: (Diya)
Connect Software and Hardware |  |  | March 2022 31: (Charles)
Final System Testing |  |  | March 2022 7: (Diya)
Work on Project Appearance |  |  | March 2022 7: (Charles)
Final Demo |  |  | March 2022 7: (Mayank)
Review Formal Report | bar: March 2022 29 to March 2022 7